## Programming
Title | Tackled by | Progress | Debugged | Description
Weapon Superclass |  |  |  | Superclass for all weapons
Weapon 1 |  |  |  | Weapon that operates on the floor level
Weapon 2 |  |  |  | Weapon that operates on the second level
Weapon 3 |  |  |  | Weapon that operates on the ceiling
Player Jump |  |  |  | Have the players gravety invert if they are touching a surface, and hit the jump key
Player X-Y Movement |  |  |  | Have the player able to move around on the levels
Floor Health | Zach | In Progress |  | Code to determine if the floor breaks or not
Bullets |  |  |  | Prefabs that spawn when fired from weapon
UI Scripting |  |  |  | Code to update the UI with the game state
Main Menus |  |  |  | Simple menus to start game in 1P or 2P mode and show credits
Adding Music and Sound Effects |  |  |  | Code to ensure that music plays and sound effects activate as needed
Round Tracking | Zach | In Progress |  | Show current score on Screen as to number of rounds won by each player
Player Elimination |  |  |  | Code to end the current round by player falling out of area
Enemy AI Sensors |  |  |  | Giving an AI the ability to detect and track the player
Enemy AI State Machine |  |  |  | A set of rules for the AI to follow when player is detected and when it is not

## Art
Title | Tackled by | Progress | Verified | Description
Mood Board |  |  |  | A general mood board that will cover the overall feel of the game
Floor Prefabs |  |  |  | A prefab unit that will be used for each floor tile
Character Models |  |  |  | A rigged model for the players that will be animated for motion
Level Layout |  |  |  | The setup of the tiles for each of the 3 areas
Splash Screen |  |  |  | A welcome screen that gives a feel of the game
Main Menu Art |  |  |  | A menu screen that proceeds to either 1 player or 2 player game or shows credits
Mini Map GUI |  |  |  | A mini map that indicates players vertical location and orientation
Weapon GUI |  |  |  | Shows user current weapon as well as ammo count (possible reload bar showing reload time)
Round GUI |  |  |  | GUI showing current score between players
End Game Screen |  |  |  | Screen showing winner and loser with respective scores
Floor Destruction Animation |  |  |  | Animation for when floor tiles get destroyed
Bullet Impact |  |  |  | A bullet impact effect for player blocking
Weapon Model |  |  |  | A model for the weapons
Bullet Model |  |  |  | A model for bullets
Floor Glowing Animations |  |  |  | A gentle pulse for floor tiles
General Particle Effects |  |  |  | Particle effects for weapons firing and possible player trails